## Slide 1
Project ATLAS → BDB
Step-by-step migration plan
Cisco Secure Access — TAC Diagnostics
Assessment based on a measured Phase 0 spike, not an estimate

## Slide 2
Verdict
Both risks that could have stopped this are now closed
CLOSED
Packet parsing without tshark
dpkt replaces tshark and runs 2.5–9.6× faster, with parity on structure, headers and flow discovery.
CLOSED
UI hosting on BDB
BDB serves task files as a CDN and runs full ES-module JavaScript. Atlas is vanilla JS — near drop-in.
REMAINING
TLS parsing
Every Gate E failure traces here. Bounded, well-understood work.
Migrate it.
The analysis layer — atlas_core, where the value actually sits — has no framework imports and ports untouched. What is left is a TLS parser, a template rewrite, and mechanical task decomposition.
This is a re-platforming with a real rewrite in the middle, not a lift-and-shift.

## Slide 3
What ATLAS is today
~35,000 lines of application code, in production use for TAC escalations
Component | Role | Stack
DartHawk | DART bundle analysis — what the endpoint was configured to do | Flask + Jinja2, ~9k Py / 7.5k JS
Capture Inspector | PCAP / HAR analysis — what it actually did on the wire | FastAPI, ~5.5k Py
atlas_core | Correlation, flow joins, multi-vantage path stitching | Pure Python, ~3k
Web shell | One origin over both engines | FastAPI + a2wsgi bridge
Frontend | Vanilla JS, no build step, Tailwind via CDN | ~18,600 lines
The division that matters: the bundle is a declaration, the capture is a measurement. ATLAS reports where the two disagree — which neither artefact can establish alone.

## Slide 4
What BDB provides
Verified against the API docs, the python3.13 package list and the Full Stack tutorial
Capability | Mechanism
Frontend hosting | Task-root files served as a CDN at /app/<task> and /app_dev/<task>
Custom JS / CSS | Full ES modules. Harbor UI kit available. Nothing sanitised
Backend calls | POST /api/v2/jobs/<task>, sync or async. Same-origin bdb_cookie auth
File upload | POST /api/v2/files — multipart/form-data, 10 GB per file
Session state | Session folder persists across runs, addressed by sub_path
TAC integration | Pull a case attachment straight into the session folder by SR id
Code sync | Every task has an auto-created GitHub repo + pushpull endpoint
Packages | dpkt, scapy, haralyzer, python-evtx, lxml, pandas, plotly
Absent: Flask, FastAPI and a2wsgi. This is the single reason the web layer cannot come across unchanged.

## Slide 5
Phase 0 — what was measured
A dpkt reader built and compared against tshark over six real captures
Gate | What it checks | Result
A — Structural | Same flows discovered | PASS on 4 of 6 after fixes
B — Headers | Addresses, ports, ISN, byte counts | 100% on 4 of 6
C — TLS | SNI, version, ALPN | FAILS — the remaining work
D — Derived | Retransmits, zero-windows, RTT | 97.5–100%
E — Conclusions | Do verdicts change when the reader is swapped? | Path stitching invariant; correlation fails on TLS
Performance | Throughput vs tshark | 2.5–9.6× FASTER
Four real defects found and fixed during the spike:
Flow orientation (absent a handshake, the lower port is the listener) · port reuse splitting · gzipped captures · an idna decode that silently swallowed every SNI.

## Slide 6
Target architecture
Start as ONE task with an action input; split later if needed
ATLAS today | On BDB | Effort
FastAPI web shell | Gone — BDB serves the frontend | Delete
Capture Inspector static HTML/JS/CSS | Copy to task root | Drop-in
Shell assets, design tokens | Copy to task root | Drop-in
atlas_core (correlation, path) | Unchanged — no framework imports | None
DartHawk Jinja2 + Flask | Static HTML, rendering moved client-side | REWRITE
Routes /upload, /flows, /flow | action values on the task | Mechanical
In-memory capture store | Session folder + subPath | Small
Tailwind via public CDN | Vendor as a task file | Small — fixes an existing bug
tshark | dpkt | TLS parser outstanding

## Slide 7
Step-by-step plan
Sequenced so the unknowns die earliest
0
Vertical slice
DART bundle in → health snapshot rendered. No tshark needed. Exercises upload, task invocation, CDN frontend, JSON round-trip and rendering all at once.
1
Finish the packet layer
TLS parser with segment reassembly. Re-run Gate E until correlation is invariant. Fix the gzip capture. Prove the ISN join.
2
Split backend into task actions
analyze_bundle, capture_flows, flow_detail, correlate, path_stitch. Boundaries already exist as routes.
3
Frontend port
Copy static assets, vendor Tailwind, rewrite DartHawk templates client-side, repoint fetch calls at the jobs API.
4
State and TAC integration
Session folder wiring, then pull bundles straight off a case by SR id.

## Slide 8
Task configuration
What to set when creating the BDB task
Field | Value | Why
name | atlas | Becomes the app URL: /app_dev/atlas
service type | python3.13 | Has dpkt, scapy, python-evtx, haralyzer
public | CHECKED | Required — the web app will not serve otherwise
contributors | TAC teammates | Who else may run it
inputs | Set via API, not by hand | bdb.json is not directly editable
Inputs for the slice
action — select: analyze_bundle | capture_flows | flow_detail | correlate
bundle — inputFile, the DART ZIP
sub_path — text, optional, points at a file already in the session folder

## Slide 9
Moving the code
Normal git — not copy-paste into a web editor
1. Create the task in BDB
2. BDB auto-provisions a GitHub repo
3. Grant repo access, then clone
4. Port code, commit, push
5. pushpull/pull syncs into BDB
6. Save → /app_dev · Deploy → /app
Two separate repositories
amarora2_cisco/Atlas — stays the upstream source of truth.
The BDB task repo — a deployment target, populated with the ported subset.
Whether they stay in sync, or the BDB repo becomes the real home, is a decision to make deliberately — but not before the slice proves out.

## Slide 10
Open risks and unknowns
Stated plainly so none of these arrive as a surprise
TLS keylog decryption is lost
tshark uses the full Wireshark TLS stack. Nothing in pure Python comes close. Confirm this is acceptable now, not mid-rewrite.
The ISN cross-vantage join has never executed
proved_hops = 0 for both readers — the test captures share no traffic. It is the linchpin of the path claim and is still unproven.
Job execution timeout unconfirmed
The last open unknown. dpkt running 2.5–9.6× faster than tshark makes this unlikely to bite, but it is not yet measured.
One gzipped capture yields zero flows
Opens and reports Ethernet encapsulation correctly, but produces nothing. Unresolved.
DartHawk template rewrite
The only genuine frontend rewrite. Bounded, but it is real work rather than a copy.

## Slide 11
Next actions
# | Action | Owner
1 | Create the BDB task — python3.13, public checked | Amit
2 | Confirm repo access and share the clone URL | Amit
3 | Decide: is losing TLS keylog decryption acceptable? | Amit
4 | Build the vertical slice — bundle in, snapshot out | Agent
5 | TLS parser, then re-run Gate E to invariance | Agent
6 | Source a same-traffic capture pair to prove the ISN join | Amit / Agent
Full detail: docs/BDB_MIGRATION_PLAN.md in the ATLAS repository (commit 6f56806).